## Slide 1: Practice Managers Forum [M365(N365) Report]
GP / Primary Care
Northwest London ICB
May 2024

## Slide 2: Introduction
‘N365’ (now M365) is the agreement between Microsoft and NHS England to provide access to the most up to date Microsoft 365 product suite.
Transitioning NWL Primary Care and NWL Corporate to the use of the Microsoft 365 product suite involves three stages:
  Data migration to the N365 environment (Microsoft Cloud i.e. Personal Files to OneDrive)
  Data migration to the N365 environment (Microsoft Cloud i.e. Shared Data to Teams)
  The implementation of EM&S tools (Microsoft Intune for end user device management)

## Slide 3: N365 (M365) Background
N365 is the agreement set out by NHS England to provide access to the most up to date Microsoft 365 product suite
N365 participation agreement to join NHS shared tenant signed by NWL CCG
July
2020
8 CCGs merge to form NWL Collaboration of CCGs
April
2021
OneDrive 95% deployed
Teams Piloting underway
Intune Piloting starting
N365 project is initiated
May
2021
March 2021
May
2024
Present
Microsoft 365 licenses procured from NHSE
September
2020
Windows 10 migration in progress
N365 mobilisation process begins
Winter 2020
Notes: This slide aims to answer: How did we get to the current state? What’s the historical context of the project?
Key Questions
  Why have we chosen to go down the shared tenant route (vs individual tenant)?
  What are the limits of the shared tenant?

## Slide 4: Project Scope
8000+ users
~368 GP Practices with individual domains
850+ users
Consolidation of 8 CCG’s data into a single CCG
1. Migrate data to Microsoft 365 environment from legacy containers.
2. Implement EM&S by enrolling devices into Azure Active Directory.
3. Decommission all primary care file servers including local domain infrastructure.
1. Migrate data to Microsoft 365 environment from legacy containers.
2. Implement EM&S through a hybrid join using TANSync.
3. Simplify corporate file server infrastructure.
NWL Primary Care
NWL Corporate
Deliverables
Deliverables
Notes: This slide aims to answer: what is in scope of this project? What needs to be achieved?

## Slide 5: Key Benefits of N365
People
Process
Technology
Improved data security from EM&S
Collaboration and co-authoring
Remote Access
Intune & Autopilot to reduce cost for device rollouts
Simplified infrastructure, reduced complexity
Significant cost savings from server decommissioning
Intune to streamline and futureproof device management
Reduced on-site engineer support burden
Enables flexible and mobile workforce
Notes: This slide aims to answer: what are the benefits we want to realise?
Expand on the security element:
EMS includes:
AAD = secure identity and access mgmt.
Intune = access management, data protection
Various security features that are advertised but not sure if they’re allowed in the shared tenant:
  Conditional access policies
  Windows Information Protection
  Defender for Cloud
  Security baselines
  DLP

## Slide 6: Vision for the Future
As Is
To Be
Local file servers
Widespread use of local file servers for chaotic, legacy and archived data & manual backup processes.
All GP local file server infrastructure is decommissioned.
Simplification of Corporate infrastructure.
Other data locations
Frequent instances of GP practices storing practice data in non-NHS storage solutions (e.g. personal OneDrive, personal Dropbox).
All GP practice and corporate data is stored in NHS approved and assured cloud storage in Microsoft 365 only.
Minimal use of Teams for data storage across GP and corporate.
All GP practice shared data to be stored in Microsoft Teams / SharePoint.
Notes: This slide aims to answer: where are we now? What is our vision for the future?
Brief overview of what intune is
Centralised management of endpoints
Mention of corporate side
Why use all these different tools?
They are the Microsoft 365 suite that we are entitled to

## Slide 7: Vision for the Future
As Is
To Be
Local file servers
Widespread use of local file servers for chaotic, legacy and archived data & manual backup processes.
All GP local file server infrastructure is decommissioned.
Simplification of Corporate infrastructure.
Other data locations
Frequent instances of GP practices storing practice data in non-NHS storage solutions (e.g. personal OneDrive, personal Dropbox).
All GP practice and corporate data is stored in NHS approved and assured cloud storage in Microsoft 365 only.
Minimal use of Teams for data storage across GP and corporate.
All GP practice shared data to be stored in Microsoft Teams / SharePoint.
Minimal use of SharePoint across GP practice estate.
Some SharePoint use in corporate.
SharePoint used as advanced UI for Microsoft Teams.
Some corporate departments and larger primary care orgs have autonomy to manage their own SharePoint sites.
All GP practice devices (Android, iOS & Windows) are secured and centrally managed by Microsoft Intune.
Users can log onto any device with NHSMail credentials.
GP local domains can be decommissioned.
Corporate is hybrid joined.
EMS including Microsoft Intune not implemented across GP or Corporate estate.
All GP practice and corporate user personal data stored in Microsoft OneDrive.
Mixed use of OneDrive for data storage across GP and corporate.
Notes: This slide aims to answer: where are we now? What is our vision for the future?
Brief overview of what intune is
Centralised management of endpoints
Mention of corporate side
Why use all these different tools?
They are the Microsoft 365 suite that we are entitled to

## Slide 8: User Experience (UX)
Current Experience
Future Experience
GP Practice Manager
Visiting Locum
“My team can securely access all the data they need from Microsoft Teams or OneDrive, wherever they are, from any secured device.”
“…my team can’t share anything across the five practices…”
“Visiting locums are often using a generic, shared Windows account to login to practice PCs…”
“Locums can log onto any NHS device in North West London with NHSMail credentials and securely access all of their personal user data.”
Notes: This slide aims to answer: how will the user experience change, if we get to where we want to be?
Locums will eventually be able to log in with their NHSMail credentials to any practice that was on the Shared Tenant’s AAD.
This could even be outside of NWL.

## Slide 9: Project Responsibilities (1/2)
Area | NWL Projects Responsibilities | Primary Care Organisation Responsibilities
Training | Deliver training to IT leads and wider end user base. | Users to attend training (recommended mandatory)
Data Ownership | Enabler / Service provider only. | Data Controller /owner (Joint Controller is NHS Digital) Note: Accenture & Microsoft are Data Processors
Data Cleansing | Responsible for excluding certain file types (.exes, etc) from migration to the Microsoft 365 environment for security reasons. | GP Practice responsible for cleansing and managing practice data pre or post-migration.
Data Migration | Responsible for full technical implementation; Pre-flight checks Technical migration process Migration QA reporting | Must sign-off to agree migration process.
Notes: This slide aims to answer: where do roles & responsibilities lie for the primary care migrations?
SPMT = SharePoint Migration Tool
Excluded File types from OneDrive include *.exe, *.lnk, *.msi,, *;dll, *.sys, *.drv, *.ldf, *.mdf, *.iso, *.bat, *.ebd

## Slide 10: Project Responsibilities (2/2)
Area | NWL Projects Responsibilities | Primary Care Organisation Responsibilities
Migration Support | Provide an escalation route for GP practices and an immediate support function post-migration. | Local Admins are empowered to provide desk side support.
Data Security | Replicate or improve data security in terms of access permissions and technical security for Shared Data and Personal Data. | Responsible and have autonomy over their Microsoft 365 environment post-migration, including: Management of Microsoft Teams memberships Teams channel structures Folder structures within channels Merging data from multiple practices into one Team
Device Management | Deploy a centralised device management organisation to manage all primary care devices via Intune. | Life-cycle management of NW London CCG supplied assets.
Notes: This slide aims to answer: where do roles & responsibilities lie for the primary care migrations?
SPMT = SharePoint Migration Tool
Excluded File types from OneDrive include *.exe, *.lnk, *.msi,, *;dll, *.sys, *.drv, *.ldf, *.mdf, *.iso, *.bat, *.ebd

## Slide 11: Project Risks: People
IT leads and GP staff concerns around Information Governance (IG).
End-user disruption from new ways of working.
IT leads lack appropriate skills to support end users.
Risk
Probability
(1-5)
Impact
(1-5)
Mitigation
Further Info
Risk Score
5
4
3
3
3
3
15
12
9
Acceptable use policy, share findings from DPIA assessments (NHSE, NWL) and echo IG assurance from NHSD.
Support during migration process, training packs and videos (Akari).
Escalation route for support provided during migration.
Risk identified during discovery phase – primary care orgs want assurance from NHSE that they can securely put their data into the cloud.
Impact is mainly around shared data move and working with files and folders through the Teams UI.
Large variety between different primary care IT leads in terms of IT competency and support capability.
Notes: This slide aims to answer: What are the risks and challenges faced around the ‘people’ element of the project?

## Slide 12: Project Risks: Process
Inadequate support capacity or capability in the BAU organisation once project is handed over.
Inadequate support capacity or capability in the project organisation during migration process.
There is unknown funding for N365 licensing.
Risk
Probability
(1-5)
Impact
(1-5)
Mitigation
Further Info
Risk Score
3
3
2
3
3
3
9
9
6
Engage ops teams to develop BAU support organisation. Monitor resource requirements.
Plan to develop project support organisation.
Forward notification of NHSE funding.
Reskilling or bringing in new resource may be required.
This should be developed alongside the project.
Does project support have capacity to scale up to ~400 primary care data migrations?
Potential to fund from revenue budget.
Notes: This slide aims to answer: What are the risks and challenges faced by the ‘process’ element of the project?

## Slide 13: Project Risks: Technology
Risk
Probability
(1-5)
Impact
(1-5)
Mitigation
Further Info
Risk Score
Inconsistent and challenging technical environments in primary care group policy (GP) due to recent mergers.
Microsoft Office Licensing over multiple devices.
Unclear technical environment within the Shared Tenant, particularly around EMS.
4
3
4
3
3
4
12
9
12
Pre-flight checks before migration technical work occurs to ensure healthy GP environment.
To be tested during shared data migration testing phase.
Continued discovery work and testing processes.
Unhealthy GP practices to be identified and migrated in separate phase.
Locums or visiting N365 users may consume an O365 apps for enterprise license by logging onto a new computer.
Technical discovery phase with delivery partner (Virtual Engine).
Data loss occurs during the migration process.
1
5
5
Practice Manager sign-off in advance of migration & QA process to report on data migrated.
Data is only copied so there will always be a backup, even if the migration fails. Data loss could only happen via operator error.
Notes: This slide aims to answer: What are the risks and challenges faced by the ‘technology’ element of the project?

## Slide 14: Further Considerations: Data Security
Data Security Considerations | Current State Individual Local File Servers | Future State NHS Shared Tenant (Microsoft Public Cloud)
Access Permissions | Large variation across practices. Some shared folders with restricted access. | Replicated access permissions through Teams and channels membership. Replicated access permissions through SharePoint access restrictions.
Security Products | Inconsistent patching processes. Inconsistent 3rd party products installed. No disk encryption in place. | Default Microsoft Cloud Security Products Defender for Cloud. Microsoft Endpoint for Office. Microsoft Active Threat Protection. No single point of failure (Disaster Recovery). Endpoint Security Conditional access policies. Baseline security policies. Intune functions: remote wiping and remote locking of devices. App protection policies for BYOD devices. Automatic data retention policies (details pending from NHSE). Data Loss Prevention (details pending from NHSE).
Shadow IT | Use of unsupported 3rd party products: Dropbox Personal OneDrive accounts | Reduced shadow IT through the implementation of the NHS-supported N365 environment.
Notes: This slide aims to: zero in on the data security element. What risks are there to data security? How are we improving security (or - at minimum - replicating current levels of security)
Slide under construction

## Slide 15: Further Considerations: Cost Savings
Future State ( e.g. Primary Care indicative)
Current State ( e.g. Primary Care indicative)
Analysis on cost savings from server decommissioning and reduced support overhead. Productivity gains not included
Item | Annual | 3 years
Support | £450,000 | £1.35m
Hardware Software | £400,000 | £1.2m
Total | £850,000 | £2.5m
Item | Annual | 3 years
Support | £120,000 | £360,000
Hardware Software | £550,000 | £1.65m
Total | £750,000 | £2.01m
£300,000 = Indicative Total costs savings over three years
Notes: This slide aims to: zero in on the data security element. What risks are there to data security? How are we improving security (or - at minimum - replicating current levels of security)
Slide under construction

## Slide 16
Where are we now – May 2024

## Slide 17: M365 Plan On A Page – GP Practices (SG4-Testing & Validation) (SG5-Deliver & Transition to Support)
Dec’ 23 (Q3) | Jan’ 24 – March 24 (Q4) | April 24 – June 24 (Q1) | July 24 – Sept’ 24 (Q2) | Oct’ 24 - Dec’ 24 (Q3) | Jan’ 25 – March 25 (Q4)
OneDrive - (GP)
Training Developed & Made Available
Teams Structures Agreed & Migration Approach Defined
Intune - (GP)
Sites = same 8 used for Teams
Intune Deployment Approach developed & tested
Scheduling Go lives
Shared Data Migration
-File shares identified
-Security groups identified
April 2024 Migrations Completed
Teams - (GP)
Personal Data migrated to M365
Shared Data migrated to M365
End User Device Mgmt
Core apps published
3rd party apps published
M365 Office deployed.
Local Servers decommissioned
Transition to Support
Teams Piloting (UAT)
Initial UAT using model office set-up at MBR – training defined
OneDrive Migration
May 2024: Transition to Support completed
Teams Migration
April’ 2025 Migrations Completed
May 2025: Transition to
Support completed
Transition to Support
Intune Piloting (UAT)
Intune Migration
April 2025 Migrations Completed
Transition to Support
Server decommissioning
Sept 2025
complete
Training Continual Improvement
8 sites selected
Intune Deployment Blueprint Approved
Refresh Team Involved with Intune deployments
May 2025: Transition to Support completed
Notes: This slide aims to answer: what is in scope of this project? What needs to be achieved?

## Slide 18: M365 Deliverables & Status – GP Practices
8000+ GP Practice users
~350 +GP Practices
1. Migrate personal and shared data to Microsoft M365
OneDrive & Teams from existing file servers
2. Deliver OneDrive and Teams User Training
3. Meet Data Protection (IG) Governance Compliance
requirements.
4. End user Device Management (Intune). Implement EM&S,
enroll end user devices into Azure Active Directory.
5. Develop a Service Support Model and deliver technical
training to IT service support staff.
6. Update the Joiners Movers Leavers process to fit with
managing staff, applications access and technical resource
7. Decommission GP Practice file servers
NWL GP Practice M365 Deliverables
NWL GP Practice M365 Status
Deliverables
~350 sites migrated to OneDrive.
325 sites transitioned to support
Training developed by Akari & published on LMS for GP’s
M365 Coms packs prepared and issued to GP PM’s as sites are scheduled for go-live.
Trai
Teams structures agreed with Practice Managers
8 Pilot sites selected
2 of the 8 Pilot sites are testing the Shared Data Migration approach
Transition to Support requirements underway.
Detailed design specification progressing for GP’s
Core GP apps published in Intune.
Test site at Willesden (K&W) running Intune
Planned pilot testing underway using same Teams pilot sites.
Status May 2024
Notes: This slide aims to answer: what is in scope of this project? What needs to be achieved?

## Slide 19
Project: M365 (N365) |  | Project Manager: SRO Sponsor: |  |  |  | Dermot Anderson Iftikhar Din |  | 
Overall summary |  |  | Return to green plan |  |  |  | Last month | This month
‘M365’ is the agreement between Microsoft and NHS England to provide access to the most up to date Microsoft Office & Microsoft product suite via the internet significantly improving secure data access, user mobility and collaboration. Transitioning NWL Primary Care users and devices to N365 portfolio of services involves three stages: Data migration of personal files from local servers to OneDrive. Data migration of shared data / folders from local servers to Teams Implementation of Microsoft Mobility & Security tools (Microsoft Intune – end user device mgmt.) replaces GP Practice local server domain control, provides single sign-on capability. The adoption of M365 will release dependency on local file servers within GP Practices As of June 1st, 2023, N365 became M365 joining the same portfolio of capabilities as standard Microsoft M365 products. |  |  | Plan returned to green since MS Server upgrade work has completed |  | Overall |  |  | 
 |  |  |  |  | Schedule |  |  | 
 |  |  |  |  | Budget |  |  | 
 |  |  |  |  | Scope |  |  | 
 |  |  |  |  | Benefit |  |  | 
Achievements since last update |  |  | Planned activities for this project stage |  |  |  |  | 
5 GP sites remain to be migrated to OneDrive. This relates to personal files. 300 sites have been file scanned for shared data folder & file layouts. This is part of preparing migration of shared data to Teams. An extract has been provided to select pilot site Primary Care PMs to agree the shared data to they wish to be migrated. The general rule for migration will be all shared date with agreed file types will be migrated. Pilot sites have been selected. Mansell Road & Crawford practices has been migrated to Teams, this is the first pilot site Ongoing: Intune piloting preparations: Piloting will follow the same set of sites as was selected for Teams Ongoing: A model office environment representing a S1 and EMIS site is to set-up in MBR for thorough application testing |  |  | Intune desktop UAT at K&W site Ongoing Ongoing Model Office set-up at MBR for Intune testing and deployment guide documentation Shared data migration @ pilot sites ongoing (2 further sites selected this reporting period out of 8 - Ongoing Teams Training Packs to be updated & circulated / posted on LMS Schedule Intune pilots at Mansell Road and Crawford Surgeries |  |  |  |  | 
Critical issues | Key risks |  |  | Mitigation |  |  |  | 
N/A | Training on M365 for end users Service Desk cannot support M365 |  |  | Training packs and end user support delivered Service transition model reflects delivery of skills training at a level of competency required to support M365 |  |  |  | 

## Slide 20: M365 Contact & Feedback
Get in touch with the N365 project team – Chat
nhsnwl.gpn365project@nhs.net
Get in touch with the N365 project team – email us
nhsnwl.gpn365project@nhs.net
Interaction and input will help the project develop an FAQ template

## Slide 21
THANK YOU